## Summary
QA Kickback Ratio Report — 2026-04-01 to 2026-04-14
Generated: 2026-04-22 04:40
Project | → In QA | In QA | Kicked Back (→ReOpen) | Ratio 1 (%) | Ratio 2 (%) | D1 JQL | D2 JQL
OBRI | 246 | 275 | 73 | 29.7 | 26.5 | project = "OBRI" AND status changed TO "In QA" DURING ("2026/04/01", "2026/04/14") | project = "OBRI" AND status was "In QA" DURING ("2026/04/01", "2026/04/14")
CJ | 51 | 58 | 12 | 23.5 | 20.7 | project = "CJ" AND status changed TO "In QA" DURING ("2026/04/01", "2026/04/14") | project = "CJ" AND status was "In QA" DURING ("2026/04/01", "2026/04/14")
OPR | 56 | 78 | 5 | 8.9 | 6.4 | project = "OPR" AND status changed TO "In QA" DURING ("2026/04/01", "2026/04/14") | project = "OPR" AND status was "In QA" DURING ("2026/04/01", "2026/04/14")
LOY | 96 | 116 | 18 | 18.8 | 15.5 | project = "LOY" AND status changed TO "In QA" DURING ("2026/04/01", "2026/04/14") | project = "LOY" AND status was "In QA" DURING ("2026/04/01", "2026/04/14")
TOTAL | 449 | 527 | 108 | 24.1 | 20.5

## Kickback Detail
QA Kickback Detail — 2026-04-01 to 2026-04-14
Project | Issue Key | Summary | Assignee
OBRI | OBRI-20199 | Android ¦ Test ¦ Apps are getting crashed after launching latest Royal and Celebrity beta | Sandip Jadhav
OBRI | OBRI-20148 | IOS ¦ Royal Test Ship ¦ Booking card and reserved tag not visible after placing reservation | Gianella Arenas
OBRI | OBRI-19974 | Service ¦ GQL¦ PLP ¦ MobileAppPLPProducts is throwing below error for shorex category on stage | Mithlesh Chouhan
OBRI | OBRI-19856 | PRD ¦ OrderHistory ¦ Hybris ¦ Title is not reflecting in OrderHistory and OrderDetails for Inactive Products | Harrison Dunnett
OBRI | OBRI-19777 | Android ¦ Dining Package ¦ The "Modify Package" CTA is disabled | Lucas Lopez
OBRI | OBRI-19771 | Web ¦ STG - Yellow ¦ PDP ¦ Conflict cancel flow on the PDP is not working as expected | Carley Montanti
OBRI | OBRI-19735 | Bundles ¦¦ iOS ¦¦ 'OrderID' is not getting retrieved in the product modification flow from calender. | Shashank Kumar Singh
OBRI | OBRI-19675 | Bundles ¦¦ Web ¦¦ Andriod ¦¦ IOS ¦¦ Not able to place order for any Bundles Package. | Piyush Jain
OBRI | OBRI-19673 | Android ¦ Stage ¦ Toggle on ¦ update cart button is not getting enabled after removing reservation conflict in modify cart | Jyothi Basavarajaiah
OBRI | OBRI-19609 | Shipboard ¦ Android ¦ Celebrity ship test¦ not able to see shorex and beverage category prod in app | Sonali Kumari
OBRI | OBRI-19586 | Search ¦ Services ¦ For search only products are returned & venues are missing . | Rachel McAuley
OBRI | OBRI-18889 | Bundles ¦ App ¦ Android ¦ Order details ¦ Route to package details from Order details screen | Sundara Manikandan
OBRI | OBRI-18176 | Services¦ Search ¦ Calling MobileAppPLPFiltersSearch with the interest or duration filter value causes the API to return an error. | Rachel McAuley
OBRI | OBRI-18018 | android ¦ Propel ¦ Android should get image for takeover screen from notification service | SUMANTH CH
OBRI | OBRI-18005 | Bundles¦ iOS ¦ Royal ¦ UI/UX ¦Incorrect toast message displayed | Lucas Lopez
OBRI | OBRI-17945 | [analytics] ¦ Bundles ¦ App ¦ Android ¦ Booking ¦ Track bundle Modification Guest screen | Vijay Prasanna R
OBRI | OBRI-17938 | Order management ¦ update original order entry status to SWAP_CANCEL_PENDING(swap order process) | Gianella Arenas
OBRI | OBRI-17922 | Hybris Pricing ¦ IBT¦ Subtotal value is not correct on checkout page and Order confirmation page for GBP currency | Venu Madhav Chintapalli
OBRI | OBRI-17912 | Hybris Pricing ¦ DB ¦ Improvement for BO to speed up QA validation -> Cart/Order Entry -> Common Tab | Lucas Lopez
OBRI | OBRI-17905 | Order management ¦ Set swap order entry status as booked and cancel original entry (swap order process) | Gianella Arenas
OBRI | OBRI-17904 | Order management ¦ Capture Payment for price increase items (swap order process) | Gianella Arenas
OBRI | OBRI-17866 | Order management ¦ Swap update order and sailing parameter action | Nagaja Vasireddy
OBRI | OBRI-17849 | Bundles ¦ App ¦ iOS ¦ Calendar ¦ View or Modify Flow | Walter Timothee
OBRI | OBRI-17821 | POS ¦ GHS ¦ Coupon does not display in GHS System | Sravani Chintakindi
OBRI | OBRI-17820 | Order management ¦ Hybris ¦ Reservation details ¦ Implement Cancelation rules in Hybris | Gianella Arenas
OBRI | OBRI-17819 | Order management ¦ Hybris ¦ Reservation details ¦ Implement Modification rules in Hybris | Gianella Arenas
OBRI | OBRI-17660 | POS ¦ Dining ¦ POS tax is disabled, tax is not included for refund | Ashok Kumar Narayana
OBRI | OBRI-17390 | Propel 1:1 Promotions ¦ Services ¦ Update graphQL filter update to add new field to take code in input | SUMANTH CH
OBRI | OBRI-17028 | PLP ¦ Android ¦ Implement Sort & Filter Screen for Search Results | Vemireddy Sambasiva Reddy
OBRI | OBRI-17027 | PLP ¦ iOS ¦ Implement Sort & Filter Screen for Search Results | Naveen Venkatesan
OBRI | OBRI-16970 | Booking flow ¦ Eligibility/Eligibility-GQL ¦ Services ¦ Conflict resolution ¦ Updates to support conflicts with dining packages | Mithlesh Chouhan
OBRI | OBRI-16969 | Booking flow ¦ Web ¦ Conflict resolution ¦ Conflict with dining packages (booked orders and items in cart) | Kaushik Mitra
OBRI | OBRI-16965 | Booking flow ¦ Android ¦ Conflict resolution ¦ Conflict with dining packages (booked orders and items in cart) | Vijay Lachwani
OBRI | OBRI-16963 | Booking flow ¦ iOS ¦ Conflict resolution ¦ Conflict with dining packages (booked orders and items in cart) | Rameshkumar KN
OBRI | OBRI-16801 | Bundles ¦ APP ¦ iOS ¦ Conflict ¦ Prevent cancellation of a conflicting item that is part of a Bundle package | Lucas Lopez
OBRI | OBRI-16361 | PLP Search ¦ Android ¦ Clarify Search Input Rules for Special Character Queries | Ravi NA
OBRI | OBRI-15478 | Dining ¦ Hybris ¦ Price override in the Booking flow | Vishal Patil
OBRI | OBRI-15422 | Booking flow ¦ Android ¦ Conflict management ¦ Show message for this reservation cannot be canceled | Gianella Arenas
OBRI | OBRI-15421 | Booking flow ¦ iOS ¦ Conflict management ¦ Show message for this reservation cannot be canceled | Gianella Arenas
OBRI | OBRI-15326 | Order management ¦ iOS ¦ Remove guests ¦ Experience when trying to remove all guests | Suma Krishnappa
OBRI | OBRI-15204 | Order management ¦ Android ¦ Remove guests ¦ Experience when trying to remove all guests | Rameshkumar KN
OBRI | OBRI-15107 | Order management ¦ Refund amount in swap order flow for price decrease entries | Gianella Arenas
OBRI | OBRI-14756 | Shipboard Dining Charges ¦ Hybris ¦ Bulk booking ¦ Display POS pricing at guest level after adding guest | Vishal Patil
OBRI | OBRI-13562 | iOS ¦ Regression ¦ Cancel reservation CTA should not be displayed if the cancellation window has passed (QA only) | Gianella Arenas
OBRI | OBRI-13377 | Shipboard Dining Charges ¦ Hybris ¦ Bulk booking ¦ Integration with POS to post charges at place orders | Vishal Patil
OBRI | OBRI-12775 | Booking flow ¦ iOS ¦ Variant selection ¦ Variants has ineligibility restrictions for selected guests | Gianella Arenas
OBRI | OBRI-12756 | Sort and Filter Dining PLP ¦ Services¦ Define Sorting Logic for Venues and Products | Rachel McAuley
OBRI | OBRI-12454 | Bundles ¦ App ¦ iOS ¦ Booking ¦ Populate "Sort&filter" screen for bundles flow | Lucas Lopez
OBRI | OBRI-10260 | Calendar ¦ Android ¦ Implement Logic for Event Card Stacking | Stephanie Bien-Aime
OBRI | OBRI-9578 | [analytics] ¦ Bundles ¦ App ¦ Android ¦ Booking ¦ Track bundle modification | Vijay Prasanna R
OBRI | OBRI-9385 | Bundles ¦ App ¦ iOS ¦ Order Management ¦ View or Modify Package CTA and Package Message | Swati YY
OBRI | OBRI-9198 | [analytics] ¦ Bundles ¦ App ¦ Android ¦ Booking ¦ Track Modify Reservation Popup | Sagine Ferrus
OBRI | OBRI-9193 | [analytics] ¦ Bundles ¦ App ¦ Android ¦ Booking ¦ Update Cart screen tracking [MVP] | Sagine Ferrus
OBRI | OBRI-9183 | [analytics] ¦ Bundles ¦ App ¦ android ¦ Booking ¦ Update Add On submission tracking [MVP] | Sagine Ferrus
OBRI | OBRI-9081 | Bundles ¦ App ¦ Android ¦ Booking ¦ Routing for guest modification confirmation modal (removing) | Doddi Aditya
OBRI | OBRI-8400 | [analytics] Bundle Booking Flow ¦ Web ¦ Update cart tracking to reflect package and addon products | Leena Patil
OBRI | OBRI-8387 | [analytics] Bundle Booking Flow ¦ Web ¦ track pageview for build my package | Sagine Ferrus
OBRI | OBRI-7475 | [analytics] ¦ Bundles ¦ App ¦ iOS ¦ Booking ¦ trackState Add to Cart Confirmation Modal [MVP] | Sagine Ferrus
OBRI | OBRI-7474 | [analytics] ¦ Bundles ¦ App ¦ Android ¦ Booking ¦ Add to Cart button tracking [MVP] | Sananda Banik
OBRI | OBRI-7473 | [analytics] ¦ Bundles ¦ App ¦ iOS ¦ Booking ¦ Update Add On submission tracking [MVP] | Valeria Federova
OBRI | OBRI-7457 | [analytics] ¦ Bundles ¦ App ¦ iOS ¦ Booking ¦ Update Variance Selection tracking [MVP] | Valeria Federova
OBRI | OBRI-7448 | [analytics] ¦ Bundles ¦ App ¦ android ¦ Booking ¦ Update AddOn PDP tracking [MVP] | Sagine Ferrus
OBRI | OBRI-5296 | Bundles ¦ Hybris ¦ IBT¦ PLP Add to Cart ¦ (QA only - Non USD) Validate bundle price rules when adding to cart an AddOn product without promo | Madhu Sudhan Reddy Takkoli
OBRI | OBRI-5295 | Bundles ¦ Hybris ¦ IBT¦ PLP Add to Cart ¦ Implement bundle price rules when adding to cart an AddOn product without promo | Madhu Sudhan Reddy Takkoli
OBRI | OBRI-4915 | Bundles ¦ App ¦ iOS ¦ Order Modify ¦ Confirm "Change day or time" of already booked reservation as part of package | Lucas Lopez
OBRI | OBRI-4900 | Bundles ¦ App ¦ iOS ¦ Order Modify ¦ Remove guest(s) confirm guest removal | Lucas Lopez
OBRI | OBRI-4262 | Bundles ¦ Web ¦ Booking ¦ Create bundle addon products PLP page | Lucas Lopez
OBRI | OBRI-3942 | Order management ¦ iOS ¦ Populate options in modify reservation pop up | Rameshkumar KN
OBRI | OBRI-3917 | Order management ¦ Android ¦ Populate options in modify reservation pop up | Vysnavi Devi Balu
OBRI | OBRI-3825 | Order management ¦ Android ¦ Disable "Modify reservation" CTA when ALL manage options = false | Gianella Arenas
OBRI | OBRI-3255 | PLP Search ¦ Android ¦ Populate & Resiliency for Search Results Based on Queries | Rachel McAuley
OBRI | OBRI-2962 | PLP Search ¦ iOS ¦ Populate & Resiliency for Search Results Based on Queries | Rachel McAuley
OBRI | OBRI-2599 | Order management ¦ Services ¦ Add Guests Conflict - change date & time conflicts | Prasanna Balla
CJ | CJ-2732 | CJ ¦ Web ¦ Fix GA-0108 AccessToken missing in services request | Brittany Chesler
CJ | CJ-2646 | GA ¦ Web ¦ Dashboard ¦ Stateroom Upgrade | Brittany Chesler
CJ | CJ-2632 | GA ¦ Web ¦ Dashboard ¦ Add Cruise Countdown For All Upcoming Cruises | Brittany Chesler
CJ | CJ-2607 | GA ¦ Web ¦ Plan My Cruise ¦ Courtesy holds CTA is navigating the user to Home Dashboard instead of Upcoming trips module from Plan My Cruise | Brittany Chesler
CJ | CJ-1406 | GA ¦ iOS ¦ Sign in ¦ Resiliency on sign in when authentication service is down | Brittany Chesler
CJ | CJ-689 | Notifications ¦ Android ¦ Mass Cancellation: Notification Takeover | Shawanda Davis
CJ | CJ-627 | GA ¦ Android ¦ Sign in ¦ Forgot Password ¦ Resiliency - Password Reset Error | Mathavan Kaliyaperumal
CJ | CJ-621 | GA ¦ Android ¦ Sign In ¦ Forgot Password ¦ Reset Password "Forgot Answer?" Mobile | Keerti Gupta
CJ | CJ-619 | GA ¦ Android ¦ Sign In ¦ Forgot Password ¦ Password Reset | Brittany Chesler
CJ | CJ-595 | GA ¦ Android ¦ Sign In ¦ Forgot Password ¦ Reset Password Email Link | Bharath KM
CJ | CJ-592 | GA ¦ Android ¦ Sign In ¦ Account Locked Screen | Pablo Valdes
CJ | CJ-441 | GA ¦ iOS ¦ Sign In ¦ Forgot Password ¦ Successful Password Reset Screen | Brittany Chesler
OPR | OPR-9581 | Room Service ¦ Web app ¦ Export to CSV | Poncho Mendoza Lara
OPR | OPR-9039 | Msg Center Web ¦ Update component on Header (Customer Journey) | Renaldo Holder
OPR | OPR-9007 | Copy ¦ Bot ¦ FAQ and Shortcut Initial Gathering | Noah Buttner
OPR | OPR-8756 | Room Service ¦ iOS ¦ Pick up my tray - service integration (update request) | Poncho Mendoza Lara
OPR | OPR-8729 | Analytics ¦ Android ¦ Itinerary ¦ Add externalCampaign Variable to entry pages - LA | Ganesh Kirubakar
LOY | LOY-12560 | [analytics] Cobrand ¦ Adobe ¦ web ¦ Correct impression new ads | Sagine Ferrus
LOY | LOY-12556 | LOY ¦ Koddi ¦ Forward koddi-correlation-id in advertisement API response | Keshwan Ramlu
LOY | LOY-12538 | Cobrand ¦ Web/Angular Bug - missing global variable values in Celebrity brand | Sagine Ferrus
LOY | LOY-12453 | Cobrand ¦ Web ¦ Commerce Web App ¦ Koddi Analytics — Impression + Click Beacons | Sean Flynn
LOY | LOY-12452 | Cobrand ¦ Web ¦ Commerce Web App ¦ Non-Cobrand Ads — Consume subtitle, adLabel, secondaryImage and title fields | Sean Flynn
LOY | LOY-12270 | CLONE - Cobrand ¦ Android ¦ Remove Program name check and replace with Program Code and Show correct Image in celebrity "Book your next Cruise"" | Sean Flynn
LOY | LOY-12012 | Cobrand ¦ iOS ¦ Non-Cobrand Ads — Consume subtitle and adLabel fields | Sean Flynn
LOY | LOY-11757 | Cobrand ¦ web¦ Book your cruise widget visibility check | Sean Flynn
LOY | LOY-11712 | Cobrand ¦ Web - Commerce Web App - Koddi Changes Required to Enable successful e2e workflow | Sean Flynn
LOY | LOY-11711 | Cobrand ¦ Web (CJ) - Koddi Changes Required to Enable successful e2e workflow | Sean Flynn
LOY | LOY-11642 | Cobrand ¦ Web (GA) - Koddi Changes Required to Enable successful e2e workflow | Sean Flynn
LOY | LOY-11578 | Cobrand ¦ Analytics ¦ react web ¦ Track interactions on the anniversary reward modal | Sagine Ferrus
LOY | LOY-11218 | Casino ¦ Services ¦ Update Loyalty.Casino-Events to create The Scheduler Flow for push notification | Devana Jackson
LOY | LOY-11216 | Casino ¦ Services ¦ Update Loyalty.Casino-Events to create The Ingestion Flow for push notification | Devana Jackson
LOY | LOY-10767 | Cobrand ¦ AEM ¦ Clean down all UI screens and communications copy with final program language (including fee disclosures) | Sean Flynn
LOY | LOY-10093 | Casino ¦ Service ¦ Implement the Construct.COH Update Partner Program for a Player endpoint | Roberto Aleman
LOY | LOY-8372 | Cobrand ¦ Analytics ¦ react ¦ Koddi - clicks ads | Cassandra Gasparin
LOY | LOY-8371 | Cobrand ¦ Analytics ¦ react ¦ Koddi - impression new ads | Cassandra Gasparin

## D1 — → In QA
D1: → In QA — 2026-04-01 to 2026-04-14
Project | Issue Key | Summary
OBRI | OBRI-20239 | Booking Flow ¦ Services ¦ AWS-TST ¦ No offerings showing for the products which are already reserved.
OBRI | OBRI-20202 | Environment ¦ Android ¦ Build not generated due to app crash
OBRI | OBRI-20201 | Services ¦ MobileAppPDPOrdersBookingCard ¦ The GQL call response is not getting updated after the order modification
OBRI | OBRI-20199 | Android ¦ Test ¦ Apps are getting crashed after launching latest Royal and Celebrity beta
OBRI | OBRI-20166 | Services ¦ TEST¦ Multivariant Age Restriction¦ Ineligible Linked guests are allowed to be selected at the Guest selection page even when both variants are age restricted
OBRI | OBRI-20148 | IOS ¦ Royal Test Ship ¦ Booking card and reserved tag not visible after placing reservation
OBRI | OBRI-20134 | Apps¦ TEST ¦ Environment is not stable, getting resiliency error while selecting any products
OBRI | OBRI-20131 | Once order placed any platform IBT, its taking more than one hour to reflect order history of web . As the app using same graphql and it should be in app also.
OBRI | OBRI-20130 | App ¦ Web ¦ some times products in PDP is throwing exception as "Something went wrong"
OBRI | OBRI-20123 | Order management ¦ Swap cart populate stock offerings details for entries in the OCC response
OBRI | OBRI-20071 | Booking Flow ¦ Android ¦ AWS - TST ¦ Guest selection and UI issue in Royal QA build
OBRI | OBRI-20057 | Sort & Filter¦ iOS ¦ Non-Dining- Toggle-ON ¦ Product card details differ from the Figma specifications..
OBRI | OBRI-20050 | Bundles ¦¦ Services ¦¦ Getting conflict on selecting unbooked time for same product in same bundle while modifying time and date
OBRI | OBRI-20036 | Test ¦ Services ¦ Orders GQL ¦ Cancelled Guest displayed for Partial cancelled Event in Calendar services.
OBRI | OBRI-20029 | Android ¦ TEST ¦ App is getting crashed while clicking any categories
OBRI | OBRI-20015 | Bundles ¦¦ Services ¦¦ Blank page or error page is coming after clicking on 'View or modify' button from a reserved product PDP page
OBRI | OBRI-20013 | IBT ¦ Tax is not included in the base price when tax roll up is set to true/False for dining products
OBRI | OBRI-20012 | Calendar ¦ Android ¦ Default to Fahrenheit/Celsius based on User Device Settings (QA Only)
OBRI | OBRI-20008 | IBT ¦ Unable to place order in TST/DEV getting "Your total is higher than you available balance."
OBRI | OBRI-19978 | Bundles¦ OCC¦ formattedDailyPrice, Daily price values displayed for bundle price is wrong
OBRI | OBRI-19977 | WEB & App ¦ Shore Test ¦ Toggle on ¦ Not able to login in test environment for Royals & Celebrity
OBRI | OBRI-19976 | IBT¦ We are not able to place orders since we are getting error as "Price has change. Please proceed with checkout" when promo is applied
OBRI | OBRI-19974 | Service ¦ GQL¦ PLP ¦ MobileAppPLPProducts is throwing below error for shorex category on stage
OBRI | OBRI-19973 | Hybris Pricing ¦ DB + IBT + OCC ¦ Total Price on Cart and Order are counting Gratuity twice for USD+MN
OBRI | OBRI-19947 | Beverages ¦ IBT ¦ For Promotional orders their is 0.01 cent differences between IBT and Fidelio
OBRI | OBRI-19856 | PRD ¦ OrderHistory ¦ Hybris ¦ Title is not reflecting in OrderHistory and OrderDetails for Inactive Products
OBRI | OBRI-19823 | Calendar ¦ Hybris ¦ OCC ¦ Calendar/OH/Itinerary Breaking for Inactive Products
OBRI | OBRI-19820 | Order History ¦ AEM ¦ GQL ¦ PROD ¦Royal_OrderDetails_Screen_Not_Displaying_FAQ_Services_FQAException
OBRI | OBRI-19817 | Bundles ¦¦ iOS ¦¦ Guest selection screen is not appearing after clicking on "Purchase now" CTA
OBRI | OBRI-19811 | Bundles ¦¦ Services¦¦ Royal & Celebrity ¦¦ After clicking on View or Modify CTA details are not being displayed
OBRI | OBRI-19803 | Calendar ¦ iOS ¦ Integrate UPDATE Reminders query
OBRI | OBRI-19799 | Calendar ¦ iOS ¦ Integrate Create Reminders query
OBRI | OBRI-19778 | Hybris Pricing ¦ DB ¦ Improvement for BO to speed up QA validation -> Cart/Order -> Positions and Prices Tab
OBRI | OBRI-19777 | Android ¦ Dining Package ¦ The "Modify Package" CTA is disabled
OBRI | OBRI-19773 | iOS ¦ My Orders ¦ My orders page is displayed with Something went wrong error when user clicks on "Select a different Cruise" CTA
OBRI | OBRI-19772 | Royal Dining¦ Toggle- ON ¦ Operating hrs status differs in iOS Vs Android.
OBRI | OBRI-19771 | Web ¦ STG - Yellow ¦ PDP ¦ Conflict cancel flow on the PDP is not working as expected
OBRI | OBRI-19747 | Bundles ¦¦ Services¦¦ Royal & Celebrity ¦¦ PDP booking card for non-bundles products are not being merged per offering
OBRI | OBRI-19740 | Order management ¦ Services ¦ Cancel Reservation details ¦ Populate cancelation reason
OBRI | OBRI-19738 | S1 ¦ OCC ¦ PLP for onboard activities is returning OCC-400 error
OBRI | OBRI-19736 | Bundles ¦ Cart-GQL¦ Hybris ¦ The Product Details is not getting updated after cancel package
OBRI | OBRI-19735 | Bundles ¦¦ iOS ¦¦ 'OrderID' is not getting retrieved in the product modification flow from calender.
OBRI | OBRI-19732 | Android ¦ Stage Toggle on ¦ Clicking on 'Okay' of Error pop-up is redirecting to previous page instead of previous step
OBRI | OBRI-19678 | PLP Search ¦ iOS ¦ Day Port Missing from Product Card during Discovery Search
OBRI | OBRI-19675 | Bundles ¦¦ Web ¦¦ Andriod ¦¦ IOS ¦¦ Not able to place order for any Bundles Package.
OBRI | OBRI-19673 | Android ¦ Stage ¦ Toggle on ¦ update cart button is not getting enabled after removing reservation conflict in modify cart
OBRI | OBRI-19652 | Order History ¦ iOS ¦ Typo on My Orders Screen
OBRI | OBRI-19648 | Test ¦ Services ¦ Orders GQL ¦ Partial cancelled Event is not reflecting in Calendar
OBRI | OBRI-19646 | HYBRIS ¦ Ship ¦ Dining Package ¦ Composite Booking ¦ Services is sending BookingModification= False for Dining package products
OBRI | OBRI-19629 | Regression ¦ STG ¦ OrderHistory ¦ Services ¦ Title is not reflecting in OrderHistory and OrderDetails for Mass cancel Order
OBRI | OBRI-19628 | Dining ¦ Hybris ¦ Prices are not reflecting in the PLP screen for dining - royal app for both IOS and android
OBRI | OBRI-19626 | Android ¦ Royal Dining¦ Toggle- ON ¦ Default sorting differs in iOS Vs Android on dining PLP.
OBRI | OBRI-19614 | Android ¦ Royal Dining¦ Toggle- ON ¦ Price Sorting is not working as expected..
OBRI | OBRI-19609 | Shipboard ¦ Android ¦ Celebrity ship test¦ not able to see shorex and beverage category prod in app
OBRI | OBRI-19586 | Search ¦ Services ¦ For search only products are returned & venues are missing .
OBRI | OBRI-19550 | Android ¦ Test ¦ Calendar ¦ Event card is truncated when there is single event card
OBRI | OBRI-19543 | Hybris ¦ STG ¦ Upcoming reservations - Spa ¦ compositeBookings ¦ The Multivariant card products are not displaying the correct product
OBRI | OBRI-19542 | Services ¦ STG ¦ Upcoming reservations/PDP ¦ The same booking card is displayed in two different multivariant Spa products
OBRI | OBRI-19536 | Hybris Pricing ¦ DB ¦ D1 - cartCalculationV2FeatureFlag = false regression testing (QA only)
OBRI | OBRI-19535 | Shipboard Beverage Pkg ¦ Hybris ¦ GHS call is not made for complimentary/price override bookings
OBRI | OBRI-19533 | Calendar ¦ Services ¦ Include Creation timestamp for reminders
OBRI | OBRI-19503 | Order History ¦ Android ¦ Update Resiliency Screen to match iOS
OBRI | OBRI-19502 | Time Based Multi Variants ¦ Services ¦ MobilePLPListDining and Product GQL ¦ Send prices for complimentary and A La Carte with base price for PLP
OBRI | OBRI-19498 | Bundles¦ IBT¦ We are not able to place orders since we are getting error as "Price has change. Please proceed with checkout"
OBRI | OBRI-19495 | Bundles ¦¦ Services ¦¦ orders-graphql ¦¦ 'View or modify' button section is not showing for a reserved package
OBRI | OBRI-19484 | Bundles ¦ Pick X ¦ OCC ¦ Expose bundle availability (bundleAvailableForBooking) for Bundle Package API call
OBRI | OBRI-19481 | Order History ¦ iOS ¦ Dining Packages ¦ Route from My Reservations to PDP when order management is toggled off
OBRI | OBRI-19478 | Order History ¦ Android ¦ Dining Packages ¦ Route from My Reservations to PDP when order management is toggled off
OBRI | OBRI-19223 | Order History ¦ Services¦ AEM ¦ GQL ¦ PROD¦Celebrity_OrderDetails_Screen_Not_Displaying_FAQ_Services_FQAException
OBRI | OBRI-19221 | Bundles ¦ App ¦ Android ¦ Order Modify ¦ Updates to "Package details" screen for dining packages
OBRI | OBRI-19219 | Shipboard Dining Charges ¦ Hybris ¦ Revise Caching Strategy
OBRI | OBRI-19216 | POS ¦ No reference number returned however, entitlement should still be created
OBRI | OBRI-19125 | Calendar ¦ Android ¦ Mapping Offerings for Calendar R2 Recommendations
OBRI | OBRI-19124 | Calendar ¦ iOS ¦ Mapping Offerings for Calendar R2 Recommendations
OBRI | OBRI-18894 | Order management ¦ Services ¦ Reservation details ¦ Ticketing ¦ Adding fullfilment.code, fullfilment.title and fullfilment.message to the product domain and add message translation integration
OBRI | OBRI-18889 | Bundles ¦ App ¦ Android ¦ Order details ¦ Route to package details from Order details screen
OBRI | OBRI-18884 | Bundles ¦ App ¦ iOS ¦ Order details ¦ Route to package details from Order details screen
OBRI | OBRI-18879 | Propel 1:1 Promotions ¦ Services ¦ Update/remove field mappings for event and notifications
OBRI | OBRI-18864 | Android ¦ Stage ¦ New Booking Flow ¦ not able modify from cart.
OBRI | OBRI-18849 | Services ¦ Time Based Variants ¦ EligibleOfferings query to pass base product
OBRI | OBRI-18842 | Order History ¦ Android ¦ Typo on My Orders Screen
OBRI | OBRI-18376 | Hybris Pricing ¦ DB ¦ Cart/Order.Subtotal not calculating correctly when Tax Rollup is set to true (USD, USD+MN,GBP)
OBRI | OBRI-18327 | Hybris Pricing ¦ DB ¦ Cart/Order.Total Price not calculating correctly when Tax Rollup is set to false (MXN)
OBRI | OBRI-18326 | Hybris Pricing ¦ DB ¦ Order.Sailing Subtotal not calculating correct when only the Tax Rollup is set to true (USD and USD+MN)
OBRI | OBRI-18208 | Bundles ¦ Web ¦ Conflicts ¦ Booking ¦ Update summary section after guests removal
OBRI | OBRI-18203 | Hybris Pricing ¦ IBT¦ Total paid value displayed on Orders page is not including tax & Gratuity
OBRI | OBRI-18189 | Bundles¦Android ¦ Royal ¦ UI/UX ¦ Font Size of the Package
OBRI | OBRI-18176 | Services¦ Search ¦ Calling MobileAppPLPFiltersSearch with the interest or duration filter value causes the API to return an error.
OBRI | OBRI-18073 | Regression ¦ Booking ¦IOS¦ Remove guest is not working in IOS
OBRI | OBRI-18035 | Bundles ¦ Services ¦ Conflicts ¦ Order Modify ¦ EligibleOfferings GQL updates to handle guest conflicts in Order management flow
OBRI | OBRI-18018 | android ¦ Propel ¦ Android should get image for takeover screen from notification service
OBRI | OBRI-18009 | Bundles¦ iOS ¦ Royal ¦ UI/UX ¦ Blank Selected Time Card Not Visible on Date Selection Screen
OBRI | OBRI-18005 | Bundles¦ iOS ¦ Royal ¦ UI/UX ¦Incorrect toast message displayed
OBRI | OBRI-17980 | Services ¦ Eligibility¦ Multi Variant TBV ¦ Ignore age restriction's when the product is multivariant for eligibility-v2
OBRI | OBRI-17945 | [analytics] ¦ Bundles ¦ App ¦ Android ¦ Booking ¦ Track bundle Modification Guest screen
OBRI | OBRI-17944 | [analytics] ¦ Bundles ¦ App ¦ iOS ¦ Booking ¦ Track bundle Modification Guest screen
OBRI | OBRI-17938 | Order management ¦ update original order entry status to SWAP_CANCEL_PENDING(swap order process)
OBRI | OBRI-17924 | Hybris Pricing ¦ IBT¦ Bundles - Tax is not getting added to Total price displayed on checkout and order confirmation page
OBRI | OBRI-17922 | Hybris Pricing ¦ IBT¦ Subtotal value is not correct on checkout page and Order confirmation page for GBP currency
OBRI | OBRI-17921 | Hybris Pricing ¦ IBT¦ Bundle Package - Subtotal value is not correct on checkout page and Order confirmation page for MXN currency
OBRI | OBRI-17912 | Hybris Pricing ¦ DB ¦ Improvement for BO to speed up QA validation -> Cart/Order Entry -> Common Tab
OBRI | OBRI-17910 | Hybris Pricing ¦ IBT ¦ Checkout page not showing the cart subtotal with tax and gratuity rollup for GBP
OBRI | OBRI-17905 | Order management ¦ Set swap order entry status as booked and cancel original entry (swap order process)
OBRI | OBRI-17904 | Order management ¦ Capture Payment for price increase items (swap order process)
OBRI | OBRI-17866 | Order management ¦ Swap update order and sailing parameter action
OBRI | OBRI-17865 | Bundles ¦ Web ¦ Conflicts ¦ Order Modify ¦ Remove guests resolution
OBRI | OBRI-17860 | Bundles ¦ Hybris ¦ Prevent the creation of more than one price rule for same product and currency in same template
OBRI | OBRI-17850 | Bundles ¦ App ¦ Android ¦ Calendar ¦ View or Modify Flow
OBRI | OBRI-17849 | Bundles ¦ App ¦ iOS ¦ Calendar ¦ View or Modify Flow
OBRI | OBRI-17836 | Order management ¦ Swap Adjust Reconciliation Charges to E2K
OBRI | OBRI-17835 | Order management ¦ Swap Reconciliation Update Charge to E2K for Price Decrease
OBRI | OBRI-17834 | Hybris Pricing ¦ DB¦ Price rollup attribute is still displaying for Currencies
OBRI | OBRI-17821 | POS ¦ GHS ¦ Coupon does not display in GHS System
OBRI | OBRI-17820 | Order management ¦ Hybris ¦ Reservation details ¦ Implement Cancelation rules in Hybris
OBRI | OBRI-17819 | Order management ¦ Hybris ¦ Reservation details ¦ Implement Modification rules in Hybris
OBRI | OBRI-17670 | Bundles¦ iOS ¦ Royal ¦ UI/UX Mismatch:iOS Package Screen Deviates from Figma Design
OBRI | OBRI-17666 | Dining ¦ POS ¦ Tax is included in refund when it's not included to the price paid
OBRI | OBRI-17660 | POS ¦ Dining ¦ POS tax is disabled, tax is not included for refund
OBRI | OBRI-17652 | Bundles ¦ App ¦ Android ¦ Booking ¦ Conflicts ¦ Conflict resolution by removing guests (only guests in bundles)
OBRI | OBRI-17650 | Bundles ¦ App ¦ iOS ¦ Booking ¦ Conflicts ¦ Conflict resolution by removing guests (only guests in bundles)
OBRI | OBRI-17486 | Android ¦ Search ¦ Implement Venue Pricing Modal in Search PLP
OBRI | OBRI-17390 | Propel 1:1 Promotions ¦ Services ¦ Update graphQL filter update to add new field to take code in input
OBRI | OBRI-17340 | Bazaar ¦ iOS ¦ Create LaunchDarkly Toggle for Daily Planner
OBRI | OBRI-17028 | PLP ¦ Android ¦ Implement Sort & Filter Screen for Search Results
OBRI | OBRI-17027 | PLP ¦ iOS ¦ Implement Sort & Filter Screen for Search Results
OBRI | OBRI-16970 | Booking flow ¦ Eligibility/Eligibility-GQL ¦ Services ¦ Conflict resolution ¦ Updates to support conflicts with dining packages
OBRI | OBRI-16969 | Booking flow ¦ Web ¦ Conflict resolution ¦ Conflict with dining packages (booked orders and items in cart)
OBRI | OBRI-16965 | Booking flow ¦ Android ¦ Conflict resolution ¦ Conflict with dining packages (booked orders and items in cart)
OBRI | OBRI-16963 | Booking flow ¦ iOS ¦ Conflict resolution ¦ Conflict with dining packages (booked orders and items in cart)
OBRI | OBRI-16876 | Calendar ¦ iOS ¦ Implement Sticky Scroll Behavior for Long Event Cards
OBRI | OBRI-16809 | Order management ¦ iOS ¦ Update PDPMobileAppOrderBookingCard, MobileAppPDPOrdersBookingCardsDiningPackages and MobileAppOrderReservationDetails queries
OBRI | OBRI-16802 | Bundles ¦ APP ¦ Android ¦ Conflict ¦ Prevent cancellation of a conflicting item that is part of a Bundle package
OBRI | OBRI-16801 | Bundles ¦ APP ¦ iOS ¦ Conflict ¦ Prevent cancellation of a conflicting item that is part of a Bundle package
OBRI | OBRI-16361 | PLP Search ¦ Android ¦ Clarify Search Input Rules for Special Character Queries
OBRI | OBRI-16255 | Calendar ¦ Hybris ¦ OCC ¦ Expose endDateTime for the Calendar, Itinerary and Order History calls
OBRI | OBRI-15753 | Bundles¦Android¦Celebrity reservations are not sorted according to day
OBRI | OBRI-15540 | Calendar ¦ Android ¦ Display gangway up/down UI for calendar tile overlap
OBRI | OBRI-15478 | Dining ¦ Hybris ¦ Price override in the Booking flow
OBRI | OBRI-15422 | Booking flow ¦ Android ¦ Conflict management ¦ Show message for this reservation cannot be canceled
OBRI | OBRI-15421 | Booking flow ¦ iOS ¦ Conflict management ¦ Show message for this reservation cannot be canceled
OBRI | OBRI-15371 | Bundles ¦¦ APP ¦¦ Android ¦¦ Remove functionality for a product is not working in addon selection page.
OBRI | OBRI-15326 | Order management ¦ iOS ¦ Remove guests ¦ Experience when trying to remove all guests
OBRI | OBRI-15244 | Calendar ¦ Android ¦ Improvements to Location fields in Event Card
OBRI | OBRI-15243 | Calendar ¦ iOS ¦ Improvements to Location fields in Event Card
OBRI | OBRI-15204 | Order management ¦ Android ¦ Remove guests ¦ Experience when trying to remove all guests
OBRI | OBRI-15140 | Bundles ¦ App ¦ iOS ¦ Booking ¦ Unable to add add-on product to the package
OBRI | OBRI-15107 | Order management ¦ Refund amount in swap order flow for price decrease entries
OBRI | OBRI-15106 | Order management ¦ Swap Reconciliation Create Charge to E2K for Price Increase
OBRI | OBRI-14756 | Shipboard Dining Charges ¦ Hybris ¦ Bulk booking ¦ Display POS pricing at guest level after adding guest
OBRI | OBRI-14567 | iOS ¦ PLP ¦ Populate Sort & Filter Data for Discovery Search Results
OBRI | OBRI-14566 | Dining ¦ Time Based Multi Variants ¦ Complimentary and A La Carte PLP
OBRI | OBRI-14157 | Bundles ¦ iOS ¦ Order Modify ¦ Add Cancel package CTA in Package Details Modify Flow
OBRI | OBRI-14053 | Calendar ¦ Android ¦ Implement Multi-day events UI
OBRI | OBRI-14052 | Calendar ¦ iOS ¦ Implement Multi-day events UI
OBRI | OBRI-13965 | Bundles¦iOS¦The cart is showing as empty even though packages are present in it.
OBRI | OBRI-13898 | Booking flow ¦ Android ¦ Variant selection ¦ Variants has ineligibility restrictions for selected guests (Modify from cart flow)
OBRI | OBRI-13897 | Booking flow ¦ iOS ¦ Variant selection ¦ Variants has ineligibility restrictions for selected guests (Modify from cart flow)
OBRI | OBRI-13738 | Android ¦ Order Management ¦ Change Time ¦ Handle Time Conflict on Modify Reservation
OBRI | OBRI-13700 | Services ¦ Eligibility¦ Multi Variant TBV ¦ Ignore age restriction's when the product is multivariant for eliigbility-v1
OBRI | OBRI-13562 | iOS ¦ Regression ¦ Cancel reservation CTA should not be displayed if the cancellation window has passed (QA only)
OBRI | OBRI-13377 | Shipboard Dining Charges ¦ Hybris ¦ Bulk booking ¦ Integration with POS to post charges at place orders
OBRI | OBRI-12779 | Booking flow ¦ Android ¦ Variant selection ¦ Remove ineligible guests from reservation
OBRI | OBRI-12776 | Booking flow ¦ iOS ¦ Variant selection ¦ Remove ineligible guests from reservation
OBRI | OBRI-12775 | Booking flow ¦ iOS ¦ Variant selection ¦ Variants has ineligibility restrictions for selected guests
OBRI | OBRI-12756 | Sort and Filter Dining PLP ¦ Services¦ Define Sorting Logic for Venues and Products
OBRI | OBRI-12729 | Bundles¦iOS¦Getting an error for reservation
OBRI | OBRI-12455 | Bundles ¦ App ¦ Android ¦ Booking ¦ Populate "Sort&filter" screen for bundles flow
OBRI | OBRI-12454 | Bundles ¦ App ¦ iOS ¦ Booking ¦ Populate "Sort&filter" screen for bundles flow
OBRI | OBRI-12450 | Bundles ¦ App ¦ iOS ¦ Booking ¦ Populate sort/filtering section to bundle addon products PLP screen
OBRI | OBRI-12430 | iOS ¦ PLP → PDP does not open until we tap on TEXT only (not on image or nearby spacing)
OBRI | OBRI-10639 | Calendar ¦ Orders-Graphql ¦ Services ¦ OrdersGQL ¦ Implement Logic for Event Card Stacking
OBRI | OBRI-10260 | Calendar ¦ Android ¦ Implement Logic for Event Card Stacking
OBRI | OBRI-10239 | Bundles ¦ Hybris ¦ Mass refunds ¦ Refund logic for mass refunds of products/orders part of a bundle (Addon product)
OBRI | OBRI-9955 | [analytics] ¦ Bundles ¦ App ¦ android ¦ Booking ¦ Update Tracking for Bundle Conflict Resolution
OBRI | OBRI-9853 | Bundles ¦ App ¦ iOS ¦ Booking ¦ Conflicts ¦ (Resiliency) Conflict resolution by removing guests
OBRI | OBRI-9578 | [analytics] ¦ Bundles ¦ App ¦ Android ¦ Booking ¦ Track bundle modification
OBRI | OBRI-9512 | AB Test Development - 092 - RCG - Desktop & Mobile - Navigation Order Based On Booking Windows
OBRI | OBRI-9385 | Bundles ¦ App ¦ iOS ¦ Order Management ¦ View or Modify Package CTA and Package Message
OBRI | OBRI-9267 | PLP ¦ Android ¦ Search Resiliency
OBRI | OBRI-9198 | [analytics] ¦ Bundles ¦ App ¦ Android ¦ Booking ¦ Track Modify Reservation Popup
OBRI | OBRI-9194 | [analytics] Bundles ¦ App ¦ iOS ¦ Track Resiliency for guest selection screen
OBRI | OBRI-9193 | [analytics] ¦ Bundles ¦ App ¦ Android ¦ Booking ¦ Update Cart screen tracking [MVP]
OBRI | OBRI-9192 | [analytics] ¦ Bundles ¦ App ¦ android ¦ Booking ¦ trackState Add to Cart Confirmation Modal [MVP]
OBRI | OBRI-9183 | [analytics] ¦ Bundles ¦ App ¦ android ¦ Booking ¦ Update Add On submission tracking [MVP]
OBRI | OBRI-9177 | [analytics] ¦ Bundles ¦ App ¦ iOS ¦ Booking ¦ Add to Cart button tracking [MVP]
OBRI | OBRI-9081 | Bundles ¦ App ¦ Android ¦ Booking ¦ Routing for guest modification confirmation modal (removing)
OBRI | OBRI-8995 | Bundles ¦ App ¦ iOS ¦ Booking ¦ Implement logic for addon product PDP screen
OBRI | OBRI-8960 | [analytics] ¦ Bundles ¦ App ¦ android ¦ Booking ¦ Update trackState for Order Confirmation screen [mvp]
OBRI | OBRI-8881 | Bundles ¦ App ¦ iOS ¦ (Ship) Order modification rules
OBRI | OBRI-8780 | Calendar ¦ Services ¦ Implement Voyages-GraphQL query
OBRI | OBRI-8736 | Bundles ¦ Pre-set ¦ Web ¦ Bundle availability rules for booking
OBRI | OBRI-8509 | Bundles ¦ App ¦ Android ¦ Resiliency for cart modification (remove addon product)
OBRI | OBRI-8400 | [analytics] Bundle Booking Flow ¦ Web ¦ Update cart tracking to reflect package and addon products
OBRI | OBRI-8387 | [analytics] Bundle Booking Flow ¦ Web ¦ track pageview for build my package
OBRI | OBRI-7946 | [analytics] Bundles ¦ App ¦ Android ¦ Track Resiliency for guest selection screen
OBRI | OBRI-7655 | [analytics] ¦ Bundles ¦ App ¦ Android ¦ Booking ¦ Update Checkout screen tracking [MVP]
OBRI | OBRI-7497 | [analytics] ¦ Bundles ¦ App ¦ Android ¦ Booking ¦ trackState for Review Reservations screen [MVP]
OBRI | OBRI-7475 | [analytics] ¦ Bundles ¦ App ¦ iOS ¦ Booking ¦ trackState Add to Cart Confirmation Modal [MVP]
OBRI | OBRI-7474 | [analytics] ¦ Bundles ¦ App ¦ Android ¦ Booking ¦ Add to Cart button tracking [MVP]
OBRI | OBRI-7473 | [analytics] ¦ Bundles ¦ App ¦ iOS ¦ Booking ¦ Update Add On submission tracking [MVP]
OBRI | OBRI-7472 | [analytics] ¦ Bundles ¦ App ¦ android ¦ Booking ¦ Update Variance Selection tracking [MVP]
OBRI | OBRI-7457 | [analytics] ¦ Bundles ¦ App ¦ iOS ¦ Booking ¦ Update Variance Selection tracking [MVP]
OBRI | OBRI-7449 | [analytics] ¦ Bundles ¦ App ¦ iOS ¦ Booking ¦ Update AddOn PDP tracking [MVP]
OBRI | OBRI-7448 | [analytics] ¦ Bundles ¦ App ¦ android ¦ Booking ¦ Update AddOn PDP tracking [MVP]
OBRI | OBRI-7447 | [analytics] ¦ Bundles ¦ App ¦ Android ¦ Booking ¦ trackState Addon PLP Screen
OBRI | OBRI-7446 | [analytics] ¦ Bundles ¦ App ¦ Android ¦ Booking ¦ trackState Addon Selection Screen
OBRI | OBRI-6980 | Calendar ¦ iOS ¦ Create "reminders" functionality (mock data)
OBRI | OBRI-6944 | Calendar ¦ Services ¦ R3 ¦ Update Events-graphql and Core.Reminders to support the Reminder modification
OBRI | OBRI-6880 | [analytics] ¦ Bundles ¦ App ¦ iOS ¦ Booking ¦ trackState Addon PLP Screen
OBRI | OBRI-6879 | [analytics] ¦ Bundles ¦ App ¦ iOS ¦ Booking ¦ trackState AddOn Selection Screen
OBRI | OBRI-6512 | AB Test Hardening - 074 - RCG - Mobile Web - PDP Content Order
OBRI | OBRI-6504 | Bundles ¦ Services ¦ Booking ¦ Expose prices at addon product level for Addon screen
OBRI | OBRI-6502 | Bundles ¦ Products-GQL ¦ Services ¦ Booking ¦ Expose prices at addon product level for PLP
OBRI | OBRI-6449 | Bundles ¦ Web ¦ Booking ¦ Conflicts ¦ Create "Conflicting reservations" modal/popup with different rules
OBRI | OBRI-6289 | Bundles ¦ App ¦ Android ¦ Notification ¦ Create Mass cancellation Notification takeover for bundle starter order
OBRI | OBRI-6277 | Bundles ¦ Services ¦ GQL ¦ Expose pricing information for products in bundle
OBRI | OBRI-6276 | Bundles ¦ Services ¦ Delta ¦ Expose pricing information for products in bundle
OBRI | OBRI-6211 | Bundles ¦ App ¦ iOS ¦ Conflicts ¦ Booking ¦ Remove guests resolution
OBRI | OBRI-6177 | Bundles ¦ App ¦ Android ¦ Booking ¦ Conflicts ¦ Create "Conflicting reservations" screen with different rules
OBRI | OBRI-6176 | Bundles ¦ App ¦ iOS ¦ Booking ¦ Conflicts ¦ Create "Conflicting reservations" screen with different rules
OBRI | OBRI-5348 | Bundles ¦ App ¦ Android ¦ Booking ¦ Populate - For products PLP screen
OBRI | OBRI-5298 | Bundles ¦ Hybris ¦ IBT ¦ PLP Add to Cart ¦ (QA only - Non USD) Validate bundle price rules when adding to cart an AddOn product with promo
OBRI | OBRI-5297 | Bundles ¦ Hybris ¦ IBT ¦ PLP Add to Cart ¦ Implement bundle price rules when adding to cart an AddOn product with promo
OBRI | OBRI-5296 | Bundles ¦ Hybris ¦ IBT¦ PLP Add to Cart ¦ (QA only - Non USD) Validate bundle price rules when adding to cart an AddOn product without promo
OBRI | OBRI-5295 | Bundles ¦ Hybris ¦ IBT¦ PLP Add to Cart ¦ Implement bundle price rules when adding to cart an AddOn product without promo
OBRI | OBRI-5154 | Bundles ¦ App ¦ iOS ¦ Booking ¦ Display product price in product card in the addon selection screen
OBRI | OBRI-5141 | Bundles ¦ App ¦ iOS ¦ Booking ¦ Display totals in addon selection screen in the header card section
OBRI | OBRI-5137 | Bundles ¦ App ¦ iOS ¦ Booking ¦ Display prices at addon product level in addon product PDP
OBRI | OBRI-5135 | Bundles ¦ App ¦ iOS ¦ Booking ¦ Display prices at addon product level in addon product PLP
OBRI | OBRI-4935 | Bundles ¦ App ¦ Android ¦ Order Modify ¦ Replace current reservation flow of a booked package
OBRI | OBRI-4921 | Bundles ¦ App ¦ iOS ¦ Order Modify ¦ Leave the "modifying existing reservations" flow of an already booked package
OBRI | OBRI-4915 | Bundles ¦ App ¦ iOS ¦ Order Modify ¦ Confirm "Change day or time" of already booked reservation as part of package
OBRI | OBRI-4909 | Bundles ¦ App ¦ Android ¦ Order Modify ¦ Enter the "Modify existing reservations" flow
OBRI | OBRI-4900 | Bundles ¦ App ¦ iOS ¦ Order Modify ¦ Remove guest(s) confirm guest removal
OBRI | OBRI-4897 | Bundles ¦ App ¦ Android ¦ Order Modify ¦ Updates to "Reservation details" screen for product booked as part of package
OBRI | OBRI-4877 | Bundles ¦ App ¦ iOS ¦ Booking ¦ Routing for guest modification confirmation modal (adding or replacing)
OBRI | OBRI-4845 | Bundles ¦ App ¦ Android ¦ Booking ¦ Modify: Confirm "Replace current reservation"
OBRI | OBRI-4262 | Bundles ¦ Web ¦ Booking ¦ Create bundle addon products PLP page
OBRI | OBRI-3942 | Order management ¦ iOS ¦ Populate options in modify reservation pop up
OBRI | OBRI-3917 | Order management ¦ Android ¦ Populate options in modify reservation pop up
OBRI | OBRI-3847 | Order management ¦ iOS ¦ Disable "Modify reservation" CTA when ALL manage options = false
OBRI | OBRI-3825 | Order management ¦ Android ¦ Disable "Modify reservation" CTA when ALL manage options = false
OBRI | OBRI-3255 | PLP Search ¦ Android ¦ Populate & Resiliency for Search Results Based on Queries
OBRI | OBRI-2962 | PLP Search ¦ iOS ¦ Populate & Resiliency for Search Results Based on Queries
OBRI | OBRI-2599 | Order management ¦ Services ¦ Add Guests Conflict - change date & time conflicts
OBRI | OBRI-898 | Calendar ¦ Services ¦ R3 ¦ Create New Delete Reminder mutation
CJ | CJ-2739 | CJ ¦ Web ¦ Fix GA-0108 AccessToken missing in services request
CJ | CJ-2734 | Notifications ¦ Has Bought RBC Product ¦ Endpoint not working in production
CJ | CJ-2733 | Notifications ¦ Casino Loyalty ¦ Endpoint not working in production
CJ | CJ-2732 | CJ ¦ Web ¦ Fix GA-0108 AccessToken missing in services request
CJ | CJ-2731 | GA ¦ Android ¦ Sign In ¦ Account Locked Screen
CJ | CJ-2705 | [Analytics] GA ¦ Web ¦ incorrect values on link a cruise completed compleation
CJ | CJ-2699 | GA webapp ¦ Web ¦ Force redirection to CJ from old GA if flag is enabled
CJ | CJ-2698 | Value true/false for hasBroughRBC parameter giving the same data in API and dB
CJ | CJ-2656 | GA ¦ PROD ¦ WEB¦ Travel Agent bookings incorrectly show Courtesy Hold banner with “Make a Payment” CTA in Production
CJ | CJ-2655 | GA ¦ Web ¦ Add a Guest ¦ Seeing "Crown & Anchor number" instead of "Captain's Club number" for Celebrity
CJ | CJ-2647 | GA ¦ Web ¦ Add a Guest ¦ Date of Birth auto‑navigation does not advance to Day field
CJ | CJ-2646 | GA ¦ Web ¦ Dashboard ¦ Stateroom Upgrade
CJ | CJ-2645 | GA ¦ Web ¦ Invalid card number validation message is incorrect on UI
CJ | CJ-2632 | GA ¦ Web ¦ Dashboard ¦ Add Cruise Countdown For All Upcoming Cruises
CJ | CJ-2624 | GA ¦ Web ¦ Casino ¦ Hide Casino Entry For Unavailable Countries
CJ | CJ-2619 | GA ¦ Web ¦ Past cruises ¦ Show when 0 earned points to the Cruise card
CJ | CJ-2618 | PROD ¦ Web ¦ Royal /Celebrity ¦ Entire loyalty widget should be fully tappable, not just the hyperlink.
CJ | CJ-2617 | GA ¦ Web ¦ Feedback flag is not reading the correct value
CJ | CJ-2616 | PROD ¦ Web ¦ Royal/Celebrity ¦ User is not able to access Sign-in & Security / Payment methods modules (chrome - safari browser)
CJ | CJ-2607 | GA ¦ Web ¦ Plan My Cruise ¦ Courtesy holds CTA is navigating the user to Home Dashboard instead of Upcoming trips module from Plan My Cruise
CJ | CJ-2597 | GA ¦ WEB ¦ Pre-prod ¦ celebrity is navigating to old document and displaying form page 6
CJ | CJ-2466 | Profile dropdown text truncated and overflowing (Portuguese)
CJ | CJ-2310 | GA ¦ Android ¦ Sign In ¦ Forgot Password ¦ Service integration for Security Question "Submit answer" CTA validation
CJ | CJ-2309 | GA ¦ iOS ¦ Sign In ¦ Forgot Password ¦ Service integration for Security Question "Submit answer" CTA validation
CJ | CJ-1620 | Notification ¦ Service¦ Error while checking on the reservation details
CJ | CJ-1453 | Notification ¦ Services ¦ Flash Sale Controller ¦ Royal Beach Club
CJ | CJ-1417 | GA ¦ Android ¦ Sign in ¦ Residency Country Code Screen
CJ | CJ-1406 | GA ¦ iOS ¦ Sign in ¦ Resiliency on sign in when authentication service is down
CJ | CJ-1405 | GA ¦ Android ¦ Sign in ¦ Forgot Password ¦ Resiliency entering incorrect email/mobile number
CJ | CJ-1192 | GA ¦ Web ¦ deployment Prod support Akamai
CJ | CJ-1101 | GA ¦ Android ¦ Sign In ¦ Sign In Query Integration
CJ | CJ-1050 | GA ¦ Android ¦ Sign in ¦ Implement Sign in with Face ID
CJ | CJ-1049 | GA ¦ Android ¦ Sign in ¦ Implement Sign in with Touch ID Modal
CJ | CJ-689 | Notifications ¦ Android ¦ Mass Cancellation: Notification Takeover
CJ | CJ-627 | GA ¦ Android ¦ Sign in ¦ Forgot Password ¦ Resiliency - Password Reset Error
CJ | CJ-626 | GA ¦ Android ¦ Forgot Password ¦ Reset Password ¦ Make a Request and Integrate Service for Resetting/Saving Password
CJ | CJ-625 | GA ¦ iOS ¦ Forgot Password ¦ Reset Password ¦ Make a Request and Integrate Service for Resetting/Saving Password
CJ | CJ-624 | GA ¦ Android ¦ Sign In ¦ Forgot Password ¦ Successful Password Reset Screen
CJ | CJ-623 | GA ¦ Android ¦ Password Reset ¦ Create Password Requirements Component
CJ | CJ-622 | GA ¦ iOS ¦ Password Reset ¦ Create Password Requirements Component
CJ | CJ-621 | GA ¦ Android ¦ Sign In ¦ Forgot Password ¦ Reset Password "Forgot Answer?" Mobile
CJ | CJ-619 | GA ¦ Android ¦ Sign In ¦ Forgot Password ¦ Password Reset
CJ | CJ-595 | GA ¦ Android ¦ Sign In ¦ Forgot Password ¦ Reset Password Email Link
CJ | CJ-594 | GA ¦ iOS ¦ Password Reset ¦ Create Password Strength Component
CJ | CJ-592 | GA ¦ Android ¦ Sign In ¦ Account Locked Screen
CJ | CJ-562 | GA ¦ Android ¦ Sign In ¦ Loading screen
CJ | CJ-455 | GA ¦ Android ¦ Password Reset ¦ Create Password Strength Component
CJ | CJ-443 | GA ¦ iOS ¦ Sign In ¦ Account Locked Screen
CJ | CJ-441 | GA ¦ iOS ¦ Sign In ¦ Forgot Password ¦ Successful Password Reset Screen
CJ | CJ-440 | GA ¦ iOS ¦ Sign In ¦ Forgot Password ¦ Password Reset
CJ | CJ-435 | GA ¦ IOS ¦ Sign in ¦ Create Sign in with Touch ID Modal
OPR | OPR-9596 | Crash ¦ Android ¦ Exception: java.lang.NoSuchMethodError
OPR | OPR-9581 | Room Service ¦ Web app ¦ Export to CSV
OPR | OPR-9553 | Room Service ¦ Android ¦ Remove item with wrong character
OPR | OPR-9552 | Room Service ¦ iOS ¦ Remove item is only taking the first item name
OPR | OPR-9550 | Room Service ¦ Android ¦ Cart and view order with no menu image
OPR | OPR-9549 | Room Service ¦ iOS ¦ Cart and view order with no menu image
OPR | OPR-9531 | Room Service ¦ Services ¦ Preorder Orders Show Zero Pricing Initially but Different price when Editing it
OPR | OPR-9504 | Room Service ¦ Android ¦ Menu description
OPR | OPR-9474 | MSG Center ¦ Web ¦ Message list rendering the 30th day message and "Last Month" is rendered instead of "Last 30 days"
OPR | OPR-9473 | MSG Center ¦ Android ¦ Expiration days info should be displayed instead of Action Required in Expiry Tab
OPR | OPR-9421 | MSG Center Web ¦ P0 UI Bug ¦ Scroll Chaining Not Disabled
OPR | OPR-9420 | MSG Center Web ¦ P0 UI Bug ¦ Sticky Header & Tabs Not Implemented
OPR | OPR-9419 | MSG Center Web ¦ P0 UI Bug ¦ End‑of‑List Font Size Wrong (Mobile & Desktop)
OPR | OPR-9418 | MSG Center Web ¦ P0 UI Bug ¦ End‑of‑List Message Logic Across Tabs
OPR | OPR-9417 | MSG Center Web ¦ P0 UI Bug ¦ Incorrect Button Style on Empty State Refresh CTA
OPR | OPR-9416 | Room Service ¦ Server ¦ Server is not getting assigned pick up my tray order
OPR | OPR-9415 | MSG Center ¦ Web Admin ¦ Services ¦ Expose a Sorting Timestamp Field for Message Center Admin Notifications
OPR | OPR-9401 | MSG Center ¦ Web Admin ¦ Messages in dashboard not sorted in descending order
OPR | OPR-9241 | MSG Center ¦ Android ¦ Use Message Category for Deals and Offers filter
OPR | OPR-9240 | MSG Center ¦ iOS ¦ Use Message Category for Deals and Offers filter
OPR | OPR-9238 | MSG Center ¦ Android ¦ Use Include Friendly Name for Message Details Screen Heading
OPR | OPR-9235 | MSG Center ¦ iOS ¦ Use Include Friendly Name for Message Details Screen Heading
OPR | OPR-9196 | DGS ¦ Bot ¦ Biweekly Bot Response and Shortcut Enhancements
OPR | OPR-9165 | MSG Center ¦ Messages With promos_commerce Category Not Appearing Under “Deals & Offers” Filter
OPR | OPR-9134 | MSG Center ¦ Services ¦ Proxy Conflicts
OPR | OPR-9065 | Room Service ¦ Android ¦ Allergens input by guest - service integration
OPR | OPR-9039 | Msg Center Web ¦ Update component on Header (Customer Journey)
OPR | OPR-9007 | Copy ¦ Bot ¦ FAQ and Shortcut Initial Gathering
OPR | OPR-8993 | Room Service ¦ Services ¦ Live Activity Enablement
OPR | OPR-8990 | RIA ¦ Services ¦ Update RegistrationController with update endpoint
OPR | OPR-8989 | RIA ¦ Services ¦ Update RegistrationController with save endpoint
OPR | OPR-8983 | Msg Center ¦ Services ¦ Observability ▸ Out-of-memory monitoring & Splunk alerting for Novu
OPR | OPR-8982 | Msg Center ¦ Services ¦ Delete single message via endpoint
OPR | OPR-8912 | Room Service ¦ Services ¦ Scheduled orders
OPR | OPR-8787 | Room Service ¦ Preparer app ¦ Functional Documentation + Runbook
OPR | OPR-8786 | Room Service ¦ Server app ¦ Functional Documentation + Runbook
OPR | OPR-8768 | Msg Center ¦ Services ¦ Segregate messages into brands (Show Royal messages in the Royal app, Celebrity messages in the Celebrity App)
OPR | OPR-8756 | Room Service ¦ iOS ¦ Pick up my tray - service integration (update request)
OPR | OPR-8729 | Analytics ¦ Android ¦ Itinerary ¦ Add externalCampaign Variable to entry pages - LA
OPR | OPR-8709 | CXC ¦ Android ¦ Navigating to the venue page
OPR | OPR-8653 | Room Service ¦ Android ¦ Notifications & DI & LA ¦ Live Updates/Status chips routing
OPR | OPR-8652 | Room Service ¦ Android ¦ Dynamic Island ¦ Expanded Dynamic Island UI
OPR | OPR-8651 | Room Service ¦ Android ¦ Status chips ¦ Implement Status chips
OPR | OPR-7616 | Msg Center ¦ Web Admin ¦ Integrate Upload Service
OPR | OPR-7614 | Msg Center ¦ Web Admin ¦ Build Upload Form and CTA
OPR | OPR-7599 | Room Service ¦ Android ¦ Allergens input by guest UI
OPR | OPR-7453 | Room Service ¦ Analytics ¦ iOS ¦ Payment resiliency pop-up trackAction
OPR | OPR-7105 | Room Service ¦ iOS ¦ Conditional Price Display
OPR | OPR-7099 | Room Service ¦ iOS ¦ Allergens input by guest UI
OPR | OPR-6988 | RIA ¦ Android ¦ Analytics ¦ Policies and consents trackState on Kids Club Registration
OPR | OPR-6987 | RIA ¦ iOS ¦ Analytics ¦ Policies and consents trackState on Kids Club Registration
OPR | OPR-6971 | RIA ¦ Android ¦ Analytics ¦ Kids Registration Home TrackState
OPR | OPR-6694 | RIA ¦ iOS ¦ Policies Screen
OPR | OPR-6660 | RIA ¦ Android ¦ Profile EntryPoint - Analytics
OPR | OPR-6547 | RIA ¦ Services ¦ Create RegistrationController with lookup endpoint
OPR | OPR-6493 | RIA ¦ Android ¦ Policies Screen
LOY | LOY-12746 | Cobrand ¦ Web ¦ Bug - royalOne and royalOnePlus action URL not being picked up from sessionStorage
LOY | LOY-12744 | Prod ¦ Cobrand ¦ WEB ¦ Alert not generated for service failure in PROD
LOY | LOY-12732 | Cobrand ¦ WEB ¦ Commerce Web App ¦ Remove unwanted Guard for Koddi Banner and fix build issue
LOY | LOY-12724 | Cobrand ¦ WEB ¦ Guest Check-in ¦ Check the koddi banner visibility in boarding pass from customer journey
LOY | LOY-12721 | Casino ¦ loyalty-cobrand ¦ Update LOY-5221 design artifacts for parallel COH Offers pattern (construct.coh PR #45)
LOY | LOY-12716 | [AEM] Rename cobrand ad bullet field bannerImageWeb to secondaryImage
LOY | LOY-12715 | Cobrand ¦ iOS - Widget background for 45,000 points ad showing ship image
LOY | LOY-12714 | Cobrand ¦ iOS - Need to know ad placement not passing actionUrls to RN
LOY | LOY-12713 | Cobrand ¦ iOS - Widget background for resiliency is showing co-brand blue and not brand ship image
LOY | LOY-12710 | Casino ¦ Service ¦ Adjust Casino Service logs so we can observe behavior more granularly
LOY | LOY-12703 | Casino entry point is showing error message for Casino member
LOY | LOY-12620 | Cobrand ¦ Android - Calls To Retail Media Endpoint Not Being Made On Ship
LOY | LOY-12619 | Cobrand ¦ Android - Remove Duplicate Retail Media Calls From Home, Dashboard, Profile Screens
LOY | LOY-12618 | Cobrand ¦ Android - App Not Calling Correct Koddi Page IDs For Home, Dashboard, Profile
LOY | LOY-12617 | Casino ¦ iOS ¦ ReactNative package updated on 1.75.2
LOY | LOY-12589 | [Analytics] Cobrand ¦Adobe¦ Web ¦ Correct Ad Click Events
LOY | LOY-12581 | Casino¦ RN ¦ saildate should be visible on the itinerary screen,if only saildate is coming from service response without full date range
LOY | LOY-12564 | Loyalty.Cobrand ¦ APP\WEB ¦ QA ¦ Validation of Co-Brand ADS
LOY | LOY-12561 | LOYALTY.Cobrand ¦ Android ¦ Koddi ¦ Ship env not displaying ads
LOY | LOY-12560 | [analytics] Cobrand ¦ Adobe ¦ web ¦ Correct impression new ads
LOY | LOY-12556 | LOY ¦ Koddi ¦ Forward koddi-correlation-id in advertisement API response
LOY | LOY-12542 | LOY ¦ IOS ¦ Koddi ¦ Ship env not displaying ads
LOY | LOY-12540 | Cobrand ¦ Services ¦ Retail Media ¦ Ship Lab - APIGEE ship-to-shore routing missing and cobrand 5xx causes 503
LOY | LOY-12538 | Cobrand ¦ Web/Angular Bug - missing global variable values in Celebrity brand
LOY | LOY-12537 | Cobrand ¦ Web/Angular Bug - Celebrity - incorrect global variable for "brand"
LOY | LOY-12526 | Cobrand ¦ Analytics ¦ iOS ¦ Koddi - clicks ads
LOY | LOY-12523 | Casino ¦ Service ¦ Optimize COH Offers API Performance by Fetching Sailing Info per Offer
LOY | LOY-12522 | Refresh Token Logic Incorrect for 401
LOY | LOY-12520 | Cobrand ¦ Services ¦ K6 scripts, update or add endpoints that are missing or outdated
LOY | LOY-12513 | LOY ¦ Android/iOS ¦ Profile Page crashing
LOY | LOY-12509 | Casino ¦ RN ¦ Hub Terms & Conditions PDF link does not open – Club Royale T&C PDF
LOY | LOY-12508 | Casino ¦ Android ¦ Hide Casino entry points when 204 error is returned
LOY | LOY-12506 | Cobrand ¦ Web¦ Remove Progamme check and show Book Cruise for nonCH
LOY | LOY-12505 | Casino ¦ Service ¦ Offers endpoint responds in error instead of null
LOY | LOY-12463 | Cobrand ¦ React Native ¦ Koddi Analytics — Impression + Click Beacons
LOY | LOY-12461 | Cobrand ¦ Android ¦ Koddi Analytics — Impression + Click Beacons
LOY | LOY-12458 | Cobrand ¦ iOS ¦ Koddi Analytics — Impression + Click Beacons
LOY | LOY-12456 | Cobrand ¦ Web ¦ Guest Check-In ¦ Koddi Analytics — Impression + Click Beacons
LOY | LOY-12455 | Cobrand ¦ Web ¦ Guest Check-In ¦ Non-Cobrand Ads — Consume subtitle, adLabel and title fields
LOY | LOY-12453 | Cobrand ¦ Web ¦ Commerce Web App ¦ Koddi Analytics — Impression + Click Beacons
LOY | LOY-12452 | Cobrand ¦ Web ¦ Commerce Web App ¦ Non-Cobrand Ads — Consume subtitle, adLabel, secondaryImage and title fields
LOY | LOY-12451 | Cobrand ¦ Web ¦ Customer Journey ¦ Koddi Analytics — Impression + Click Beacons
LOY | LOY-12450 | 1.75 ¦ Service ¦ Domestic user is having casino account but unable to see entry point
LOY | LOY-12449 | 1.75 ¦ Service ¦ Discrepancy between Loyalty Id being displayed Web & App
LOY | LOY-12448 | 1.75 ¦ Service ¦ Adjust the logic that calculates remainTierCredits
LOY | LOY-12447 | PROD ¦ Cobrand widget ¦ Text mismatch for Royal and Celebrity
LOY | LOY-12271 | CLONE - Cobrand ¦ Android ¦ Non-Cobrand Ads — Consume subtitle and adLabel fields
LOY | LOY-12270 | CLONE - Cobrand ¦ Android ¦ Remove Program name check and replace with Program Code and Show correct Image in celebrity "Book your next Cruise""
LOY | LOY-12269 | Cobrand ¦ Prod ¦ Web ¦ Clicking on "Redeem for Onboard Credit " , "Reduce your final payment" , "Pay less for your next cruise" makes user to a different URL
LOY | LOY-12019 | Cobrand ¦ iOS ¦ Remove Progamme check and show Book Cruise for nonCH
LOY | LOY-12015 | Cobrand ¦ RN ¦ Cobrand Ads — Consume subtitle and adLabel fields
LOY | LOY-12014 | Cobrand ¦ Web ¦ Customer Journey ¦ Non-Cobrand Ads — Consume subtitle, adLabel and title fields
LOY | LOY-12012 | Cobrand ¦ iOS ¦ Non-Cobrand Ads — Consume subtitle and adLabel fields
LOY | LOY-12011 | Cobrand ¦ Services ¦ RMS ¦ Non-Cobrand Ads — Add subtitle, adLabel and locale-variant field support
LOY | LOY-12010 | CLONE - Cobrand ¦ Android - ACH is showing "Book your next Cruise"
LOY | LOY-11955 | Cobrand ¦ Web ¦ Spike ¦ Silversea - RN Hosting Analysis
LOY | LOY-11890 | Co-brand ¦ AEM ¦ Shipboard - CEL Benefits Carousel Images Missing
LOY | LOY-11873 | Casino ¦ iOS ¦ Initial Props is Not having some values
LOY | LOY-11871 | LOY ¦ VSS ¦ Enrollment failure
LOY | LOY-11867 | Loyalty ¦ Project Quack ¦ Launch Darkly ¦ Create feature Toggle for Game
LOY | LOY-11861 | Casino ¦ RN - Bundle Size Investigation - Loyalty Casino NPM Package
LOY | LOY-11757 | Cobrand ¦ web¦ Book your cruise widget visibility check
LOY | LOY-11745 | Cobrand ¦ Web(QA only) -Applynow button with actionUrl from web
LOY | LOY-11712 | Cobrand ¦ Web - Commerce Web App - Koddi Changes Required to Enable successful e2e workflow
LOY | LOY-11711 | Cobrand ¦ Web (CJ) - Koddi Changes Required to Enable successful e2e workflow
LOY | LOY-11661 | Casino ¦ Service ¦ Consuming AEM content
LOY | LOY-11642 | Cobrand ¦ Web (GA) - Koddi Changes Required to Enable successful e2e workflow
LOY | LOY-11636 | BUG ¦ Casino ¦ Analytics (R1) ¦ iOS ¦ Casino entry errorMessage firing when casion entry point is hidden with 0204 error
LOY | LOY-11601 | Casino ¦ Service¦ Service should not send available ship code for Offer with past date
LOY | LOY-11589 | Cobrand ¦ Analytics ¦ react web ¦ BUG Track interactions on the bonuses and perks screen
LOY | LOY-11588 | Cobrand ¦ Analytics ¦ react web ¦ Bug PageView modal perks
LOY | LOY-11578 | Cobrand ¦ Analytics ¦ react web ¦ Track interactions on the anniversary reward modal
LOY | LOY-11358 | Android - App is Crashing when Clicking on Pay NextCruise deposit CTA
LOY | LOY-11242 | Cobrand ¦ Prod ¦ Web ¦ CH ¦ View All benefits image section is not centered
LOY | LOY-11218 | Casino ¦ Services ¦ Update Loyalty.Casino-Events to create The Scheduler Flow for push notification
LOY | LOY-11216 | Casino ¦ Services ¦ Update Loyalty.Casino-Events to create The Ingestion Flow for push notification
LOY | LOY-11129 | Loyalty ¦ Project Quack ¦ Android ¦ Launch Darkly ¦ Consume feature Toggle for Game
LOY | LOY-11125 | Loyalty ¦ Project Quack ¦ SVC ¦ Content Service Integration
LOY | LOY-10983 | Cobrand ¦ RN ¦ (Post-Launch) Shimmer while switching cards
LOY | LOY-10767 | Cobrand ¦ AEM ¦ Clean down all UI screens and communications copy with final program language (including fee disclosures)
LOY | LOY-10367 | [Analytics] Cobrand ¦ web ¦ Track impression new ads
LOY | LOY-10093 | Casino ¦ Service ¦ Implement the Construct.COH Update Partner Program for a Player endpoint
LOY | LOY-10071 | Cobrand ¦ RN ¦ Performance Optimization for React Web
LOY | LOY-10046 | Cobrand ¦ AEM ¦ Update Content for Contact Support (redemption section) in Silversea
LOY | LOY-10044 | Cobrand ¦ AEM ¦ Non-Cardholder Content for Silversea
LOY | LOY-10043 | Cobrand ¦ AEM ¦ Cardholder Content for Silversea
LOY | LOY-9405 | Loyalty ¦ Guest Account 2.0 ¦ Foundational - Splunk Observability Cloud
LOY | LOY-8372 | Cobrand ¦ Analytics ¦ react ¦ Koddi - clicks ads
LOY | LOY-8371 | Cobrand ¦ Analytics ¦ react ¦ Koddi - impression new ads
LOY | LOY-8283 | Cobrand ¦ Web ¦ Koddi ¦ Customer Journey - New Koddi Placement for Dashboard (Page ID - 2301)
LOY | LOY-7703 | Loyalty ¦ Analytics - iOS - Silversea - Loyalty Match tab - Link Loyalty Number Fail trackAction
LOY | LOY-7701 | Loyalty ¦ Analytics - Android - Silversea - Loyalty Match tab - Link Loyalty Number Modal trackState
LOY | LOY-7699 | Loyalty ¦ Analytics - iOS - Silversea - Loyalty Match tab - Successful Link popUp trackAction
LOY | LOY-6942 | Loyalty ¦ Analytics - iOS - Silversea - Loyalty Match tab - Enrollment success / failure modal functionality
LOY | LOY-6939 | Loyalty ¦ Analytics - iOS - Silversea - Loyalty Match tab - Integrate secondary brand enrollment process
LOY | LOY-5633 | Mobile ¦ Regression ¦ iOS¦The subtext on the Join Loyalty screen is not center-aligned as per figma